## Sheet1
List of Pokemon 3D Models
Working files are the .C4D - FBX / OBJ are the Sourcefiles
Modeled |  | There is a 3D mesh of the Pokemon
Q |  | Modelquality - A subjective impression of the models appearience expressed with numbers where 1 is the lowest and 5 the highest
Textured |  | The mesh is fully and flawlessly textured, all unnescesary textures and UVW maps are removed
Split |  | The model is split in several sub-meshes so that only one texture is applied to one mesh
Rigged |  | The pokemon has a functional skeleton and is therefor ready to be animated
Animated |  | The pokemon is fully animated and ready to be exported for the app
Exported |  | The pokemon has been exported as FBX file andthe FBX file has been successfully tested on the pipeline
Issues |  | Issues that have to be fixed with priority: (s) - small , (m) - medium , (h) - high
Statistics |  |  | Modeled | Textured | Split | Rigged | Animated | Exported
|  | Done | 150 | 83 | 2 | 115 | 0 | 0
|  | in Progress | 1 | 0 | 0 | 0 | 1 | 0
|  | Todo | 0 | 68 | 149 | 36 | 150 | 151
Pic | Nr. | Name | Hight [m] | Modeled | Q | Textured | Split | Rigged | Animated | Exported | Origin | Issues
| 1 | Bulbasaur | 0.71 | Yes | 4 | Yes | Yes | Yes | in Progress | No | models-resource.com | -
| 2 | Ivysaur | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 3 | Venusaur | 2.01 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 4 | Charmander | 0.61 | Yes | 3 | No | No | Yes | No | No | models-resource.com | (m) Flametexture of the tail need to be done better
| 5 | Charmeleon | 1.09 | Yes | 3 | No | No | Yes | No | No | models-resource.com | (m) Flametexture of the tail need to be done better
| 6 | Charizard | 1.7 | Yes | 3 | No | No | Yes | No | No | models-resource.com | (m) Flametexture of the tail need to be done better
| 7 | Squirtle | 0.51 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 8 | Wartortle | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 9 | Blastoise | 1.6 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 10 | Caterpie | 0.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 11 | Metapod | 0.71 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 12 | Butterfree | 1.09 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 13 | Weedle | 0.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 14 | Kakuna | 0.61 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 15 | Beedrill | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 16 | Pidgey | 0.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 17 | Pidgeotto | 1.09 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 18 | Pidgeot | 1.5 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 19 | Rattata | 0.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 20 | Raticate | 0.71 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 21 | Spearow | 0.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 22 | Fearow | 1.19 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 23 | Ekans | 2.01 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 24 | Arbok | 3.51 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 25 | Pikachu | 0.41 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 26 | Raichu | 0.79 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 27 | Sandshrew | 0.61 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 28 | Sandslash | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 29 | Nidoran♀ | 0.41 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 30 | Nidorina | 0.79 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 31 | Nidoqueen | 1.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 32 | Nidoran♂ | 0.51 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 33 | Nidorino | 0.89 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 34 | Nidoking | 1.4 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 35 | Clefairy | 0.61 | Yes | 3 | No | No | No | No | No | models-resource.com | (m) UVW needs to be fixed
| 36 | Clefable | 1.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 37 | Vulpix | 0.61 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 38 | Ninetales | 1.09 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 39 | Jigglypuff | 0.51 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 40 | Wigglytuff | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | (s) Bodytexture on 3 different sections
| 41 | Zubat | 0.79 | Yes | 3 | No | No | No | No | No | models-resource.com | (m) UVW needs to be fixed
| 42 | Golbat | 1.6 | Yes | 3 | No | No | No | No | No | models-resource.com | (m) UVW needs to be fixed
| 43 | Oddish | 0.51 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 44 | Gloom | 0.79 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 45 | Vileplume | 1.19 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 46 | Paras | 0.3 | Yes | 4 | No | No | Yes | No | No | models-resource.com | (s) Eyedots need to be integrated in bodytexture
| 47 | Parasect | 0.99 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 48 | Venonat | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 49 | Venomoth | 1.5 | Yes | 4 | No | No | Yes | No | No | models-resource.com | (m) Textureproblems with Wings and Eyes
| 50 | Diglett | 0.2 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 51 | Dugtrio | 0.71 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 52 | Meowth | 0.41 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 53 | Persian | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 54 | Psyduck | 0.79 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 55 | Golduck | 1.7 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 56 | Mankey | 0.51 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 57 | Primeape | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | (s) Bodytexture on 4 different sections
| 58 | Growlithe | 0.71 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 59 | Arcanine | 1.91 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 60 | Poliwag | 0.61 | Yes | 3 | No | No | No | No | No | models-resource.com | (m) UVW needs to be fixed
| 61 | Poliwhirl | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 62 | Poliwrath | 1.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 63 | Abra | 0.89 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 64 | Kadabra | 1.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 65 | Alakazam | 1.5 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 66 | Machop | 0.79 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 67 | Machoke | 1.5 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 68 | Machamp | 1.6 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 69 | Bellsprout | 0.71 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 70 | Weepinbell | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 71 | Victreebel | 1.7 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 72 | Tentacool | 0.89 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 73 | Tentacruel | 1.6 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 74 | Geodude | 0.41 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 75 | Graveler | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 76 | Golem | 1.4 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 77 | Ponyta | 0.99 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) Flametexture need to be done better and UVW needs to be fixed
| 78 | Rapidash | 1.7 | Yes | 1 | No | No | No | No | No | roestudios.co.uk | (m) Flames need to be added and UVW needs to be fixed
| 79 | Slowpoke | 1.19 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 80 | Slowbro | 1.6 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 81 | Magnemite | 0.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 82 | Magneton | 0.99 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 83 | Farfetch’d | 0.79 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 84 | Doduo | 1.4 | Yes | 1 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 85 | Dodrio | 1.8 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed, heads and tails not attached
| 86 | Seel | 1.09 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 87 | Dewgong | 1.7 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 88 | Grimer | 0.89 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 89 | Muk | 1.19 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 90 | Shellder | 0.3 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 91 | Cloyster | 1.5 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 92 | Gastly | 1.3 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed and mist needs to be added
| 93 | Haunter | 1.6 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 94 | Gengar | 1.5 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 95 | Onix | 8.79 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 96 | Drowzee | 0.99 | Yes | 3 | No | No | No | No | No | models-resource.com | (m) UVW needs to be fixed
| 97 | Hypno | 1.6 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 98 | Krabby | 0.41 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 99 | Kingler | 1.3 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 100 | Voltorb | 0.51 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 101 | Electrode | 1.19 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 102 | Exeggcute | 0.41 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 103 | Exeggutor | 2.01 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 104 | Cubone | 0.41 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 105 | Marowak | 0.99 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 106 | Hitmonlee | 1.5 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 107 | Hitmonchan | 1.4 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 108 | Lickitung | 1.19 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 109 | Koffing | 0.61 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 110 | Weezing | 1.19 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 111 | Rhyhorn | 0.99 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 112 | Rhydon | 1.91 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 113 | Chansey | 1.09 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 114 | Tangela | 0.99 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 115 | Kangaskhan | 2.21 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 116 | Horsea | 0.41 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 117 | Seadra | 1.19 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 118 | Goldeen | 0.61 | Yes | 4 | Yes | Yes | Yes | No | No | models-resource.com | -
| 119 | Seaking | 1.3 | in Progress |  | No | No | No | No | No |  | (h) Model needs to be done or found
| 120 | Staryu | 0.79 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 121 | Starmie | 1.09 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 122 | Mr. Mime | 1.3 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 123 | Scyther | 1.5 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 124 | Jynx | 1.4 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 125 | Electabuzz | 1.09 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 126 | Magmar | 1.3 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 127 | Pinsir | 1.5 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 128 | Tauros | 1.4 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 129 | Magikarp | 0.89 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 130 | Gyarados | 6.5 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 131 | Lapras | 2.49 | Yes | 5 | Yes | No | Yes | No | No | models-resource.com | -
| 132 | Ditto | 0.3 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 133 | Eevee | 0.3 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 134 | Vaporeon | 0.99 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 135 | Jolteon | 0.79 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 136 | Flareon | 0.89 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 137 | Porygon | 0.79 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 138 | Omanyte | 0.41 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 139 | Omastar | 0.99 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 140 | Kabuto | 0.51 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 141 | Kabutops | 1.3 | Yes | 2 | No | No | No | No | No | roestudios.co.uk | (m) UVW needs to be fixed
| 142 | Aerodactyl | 1.8 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 143 | Snorlax | 2.11 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 144 | Articuno | 1.7 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 145 | Zapdos | 1.6 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -
| 146 | Moltres | 2.01 | Yes | 3 | No | No | Yes | No | No | models-resource.com | -
| 147 | Dratini | 1.8 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 148 | Dragonair | 3.99 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 149 | Dragonite | 2.21 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 150 | Mewtwo | 2.01 | Yes | 4 | No | No | Yes | No | No | models-resource.com | -
| 151 | Mew | 0.41 | Yes | 4 | Yes | No | Yes | No | No | models-resource.com | -

## Sheet2
Column1 | Column1
Yes | 1
No | 2
in Progress | 3
4
5

## Sheet3
Nr | Name | Modeled | Textured | Split | Rigged | Animated | Exported | Origin
--- | --- | --- | --- | --- | --- | --- | --- | ---
1 | Bulbasaur | Yes | Yes | Yes | Yes | in Progress | No | 1
2 | Ivysaur | Yes | Yes | No | Yes | No | No | 1
3 | Venusaur | Yes | Yes | No | Yes | No | No | 1
4 | Charmander | Yes | No | No | Yes | No | No | 1
5 | Charmeleon | Yes | No | No | Yes | No | No | 1
6 | Charizard | Yes | No | No | Yes | No | No | 1
7 | Squirtle | Yes | Yes | No | Yes | No | No | 1
8 | Wartortle | Yes | Yes | No | Yes | No | No | 1
9 | Blastoise | Yes | Yes | No | Yes | No | No | 1
10 | Caterpie | Yes | Yes | No | Yes | No | No | 1
11 | Metapod | Yes | Yes | No | Yes | No | No | 1
12 | Butterfree | Yes | Yes | No | Yes | No | No | 1
13 | Weedle | Yes | Yes | No | Yes | No | No | 1
14 | Kakuna | Yes | Yes | No | Yes | No | No | 1
15 | Beedrill | Yes | Yes | No | Yes | No | No | 1
16 | Pidgey | Yes | Yes | No | Yes | No | No | 1
17 | Pidgeotto | Yes | Yes | No | Yes | No | No | 1
18 | Pidgeot | Yes | Yes | No | Yes | No | No | 1
19 | Rattata | Yes | Yes | No | Yes | No | No | 1
20 | Raticate | Yes | Yes | No | Yes | No | No | 1
21 | Spearow | Yes | Yes | No | Yes | No | No | 1
22 | Fearow | Yes | Yes | No | Yes | No | No | 1
23 | Ekans | Yes | Yes | No | Yes | No | No | 1
24 | Arbok | Yes | Yes | No | Yes | No | No | 1
25 | Pikachu | Yes | Yes | No | Yes | No | No | 1
26 | Raichu | Yes | Yes | No | Yes | No | No | 1
27 | Sandshrew | Yes | Yes | No | Yes | No | No | 1
28 | Sandslash | Yes | Yes | No | Yes | No | No | 1
29 | Nidoran♀ | Yes | Yes | No | Yes | No | No | 1
30 | Nidorina | Yes | Yes | No | Yes | No | No | 1
31 | Nidoqueen | Yes | Yes | No | Yes | No | No | 1
32 | Nidoran♂ | Yes | Yes | No | Yes | No | No | 1
33 | Nidorino | Yes | Yes | No | Yes | No | No | 1
34 | Nidoking | Yes | Yes | No | Yes | No | No | 1
35 | Clefairy | Yes | No | No | No | No | No | 1
36 | Clefable | Yes | Yes | No | Yes | No | No | 1
37 | Vulpix | Yes | Yes | No | Yes | No | No | 1
38 | Ninetales | Yes | Yes | No | Yes | No | No | 1
39 | Jigglypuff | Yes | Yes | No | Yes | No | No | 1
40 | Wigglytuff | Yes | Yes | No | Yes | No | No | 1
41 | Zubat | Yes | No | No | No | No | No | 1
42 | Golbat | Yes | No | No | No | No | No | 1
43 | Oddish | Yes | Yes | No | Yes | No | No | 1
44 | Gloom | Yes | Yes | No | Yes | No | No | 1
45 | Vileplume | Yes | Yes | No | Yes | No | No | 1
46 | Paras | Yes | No | No | Yes | No | No | 1
47 | Parasect | Yes | No | No | Yes | No | No | 1
48 | Venonat | Yes | Yes | No | Yes | No | No | 1
49 | Venomoth | Yes | No | No | Yes | No | No | 1
50 | Diglett | Yes | Yes | No | Yes | No | No | 1
51 | Dugtrio | Yes | Yes | No | Yes | No | No | 1
52 | Meowth | Yes | Yes | No | Yes | No | No | 1
53 | Persian | Yes | Yes | No | Yes | No | No | 1
54 | Psyduck | Yes | Yes | No | Yes | No | No | 1
55 | Golduck | Yes | Yes | No | Yes | No | No | 1
56 | Mankey | Yes | Yes | No | Yes | No | No | 1
57 | Primeape | Yes | Yes | No | Yes | No | No | 1
58 | Growlithe | Yes | Yes | No | Yes | No | No | 1
59 | Arcanine | Yes | Yes | No | Yes | No | No | 1
60 | Poliwag | Yes | No | No | No | No | No | 1
61 | Poliwhirl | Yes | Yes | No | Yes | No | No | 1
62 | Poliwrath | Yes | Yes | No | Yes | No | No | 1
63 | Abra | Yes | Yes | No | Yes | No | No | 1
64 | Kadabra | Yes | Yes | No | Yes | No | No | 1
65 | Alakazam | Yes | Yes | No | Yes | No | No | 1
66 | Machop | Yes | Yes | No | Yes | No | No | 1
67 | Machoke | Yes | Yes | No | Yes | No | No | 1
68 | Machamp | Yes | Yes | No | Yes | No | No | 1
69 | Bellsprout | Yes | Yes | No | Yes | No | No | 1
70 | Weepinbell | Yes | Yes | No | Yes | No | No | 1
71 | Victreebel | Yes | Yes | No | Yes | No | No | 1
72 | Tentacool | Yes | Yes | No | Yes | No | No | 1
73 | Tentacruel | Yes | Yes | No | Yes | No | No | 1
74 | Geodude | Yes | Yes | No | Yes | No | No | 1
75 | Graveler | Yes | Yes | No | Yes | No | No | 1
76 | Golem | Yes | Yes | No | Yes | No | No | 1
77 | Ponyta | Yes | No | No | No | No | No | 2
78 | Rapidash | Yes | No | No | No | No | No | 2
79 | Slowpoke | Yes | Yes | No | Yes | No | No | 1
80 | Slowbro | Yes | Yes | No | Yes | No | No | 1
81 | Magnemite | Yes | Yes | No | Yes | No | No | 1
82 | Magneton | Yes | Yes | No | Yes | No | No | 1
83 | Farfetch’d | Yes | Yes | No | Yes | No | No | 1
84 | Doduo | Yes | No | No | No | No | No | 2
85 | Dodrio | Yes | No | No | No | No | No | 2
86 | Seel | Yes | No | No | No | No | No | 2
87 | Dewgong | Yes | No | No | No | No | No | 2
88 | Grimer | Yes | Yes | No | Yes | No | No | 1
89 | Muk | Yes | Yes | No | Yes | No | No | 1
90 | Shellder | Yes | Yes | No | Yes | No | No | 1
91 | Cloyster | Yes | Yes | No | Yes | No | No | 1
92 | Gastly | Yes | No | No | No | No | No | 2
93 | Haunter | Yes | No | No | No | No | No | 2
94 | Gengar | Yes | Yes | No | Yes | No | No | 1
95 | Onix | Yes | No | No | No | No | No | 2
96 | Drowzee | Yes | No | No | No | No | No | 1
97 | Hypno | Yes | No | No | No | No | No | 2
98 | Krabby | Yes | No | No | No | No | No | 2
99 | Kingler | Yes | No | No | No | No | No | 2
100 | Voltorb | Yes | Yes | No | Yes | No | No | 1
101 | Electrode | Yes | No | No | No | No | No | 2
102 | Exeggcute | Yes | No | No | No | No | No | 2
103 | Exeggutor | Yes | No | No | No | No | No | 2
104 | Cubone | Yes | No | No | Yes | No | No | 1
105 | Marowak | Yes | No | No | Yes | No | No | 1
106 | Hitmonlee | Yes | No | No | No | No | No | 2
107 | Hitmonchan | Yes | No | No | Yes | No | No | 1
108 | Lickitung | Yes | No | No | No | No | No | 2
109 | Koffing | Yes | No | No | No | No | No | 2
110 | Weezing | Yes | No | No | No | No | No | 2
111 | Rhyhorn | Yes | No | No | No | No | No | 2
112 | Rhydon | Yes | No | No | Yes | No | No | 1
113 | Chansey | Yes | No | No | No | No | No | 2
114 | Tangela | Yes | No | No | No | No | No | 2
115 | Kangaskhan | Yes | Yes | No | Yes | No | No | 1
116 | Horsea | Yes | No | No | No | No | No | 2
117 | Seadra | Yes | No | No | No | No | No | 2
118 | Goldeen | Yes | Yes | Yes | Yes | No | No | 1
119 | Seaking | in Progress | No | No | No | No | No | -
120 | Staryu | Yes | No | No | Yes | No | No | 1
121 | Starmie | Yes | No | No | Yes | No | No | 1
122 | Mr. Mime | Yes | No | No | Yes | No | No | 1
123 | Scyther | Yes | No | No | Yes | No | No | 1
124 | Jynx | Yes | No | No | No | No | No | 2
125 | Electabuzz | Yes | No | No | No | No | No | 2
126 | Magmar | Yes | No | No | No | No | No | 2
127 | Pinsir | Yes | No | No | Yes | No | No | 1
128 | Tauros | Yes | No | No | No | No | No | 2
129 | Magikarp | Yes | No | No | Yes | No | No | 1
130 | Gyarados | Yes | No | No | Yes | No | No | 1
131 | Lapras | Yes | Yes | No | Yes | No | No | 1
132 | Ditto | Yes | No | No | Yes | No | No | 1
133 | Eevee | Yes | No | No | Yes | No | No | 1
134 | Vaporeon | Yes | No | No | Yes | No | No | 1
135 | Jolteon | Yes | No | No | Yes | No | No | 1
136 | Flareon | Yes | No | No | Yes | No | No | 1
137 | Porygon | Yes | No | No | Yes | No | No | 1
138 | Omanyte | Yes | No | No | Yes | No | No | 1
139 | Omastar | Yes | No | No | Yes | No | No | 1
140 | Kabuto | Yes | No | No | No | No | No | 2
141 | Kabutops | Yes | No | No | No | No | No | 2
142 | Aerodactyl | Yes | No | No | Yes | No | No | 1
143 | Snorlax | Yes | No | No | Yes | No | No | 1
144 | Articuno | Yes | Yes | No | Yes | No | No | 1
145 | Zapdos | Yes | Yes | No | Yes | No | No | 1
146 | Moltres | Yes | No | No | Yes | No | No | 1
147 | Dratini | Yes | No | No | Yes | No | No | 1
148 | Dragonair | Yes | No | No | Yes | No | No | 1
149 | Dragonite | Yes | No | No | Yes | No | No | 1
150 | Mewtwo | Yes | No | No | Yes | No | No | 1
151 | Mew | Yes | Yes | No | Yes | No | No | 1